TERRIUM

MVP Development Timeline — July 22 to December 2026

Version 1.0 | Prepared by Claude for Smyan Reddy

# Philosophy: gated, not just dated

This timeline runs from today (Wednesday, July 22, 2026) to an MVP complete by December 1, 2026 — roughly 19 build weeks across 4 phases, with December itself reserved for a live pilot rather than more feature work. Every phase below has a hard calendar allocation AND a real completion gate borrowed directly from Terrium's own roadmap (terrium_full.docx, section 5) — the gate is what actually has to be true before the next phase starts, the dates are how much time is budgeted to get there. If a gate is met early, that time gets banked as buffer later, not spent on scope creep. If a gate slips, the buffer built into weeks 3, 8-9, and 19 is what absorbs it before December is at risk.

"Thorough and fast" is not a contradiction here: fast means no wasted motion between phases and no rebuilding the same thing twice; thorough means Phase 1 does not start until Phase 0's validation and compute-model questions are genuinely closed, not assumed. The single riskiest thing in this plan is not the engineering — it's Smyan's validation-loop and equation-pinning work staying one step ahead of Shanmuka and Victor's build work throughout. That dependency is called out explicitly in every phase below.

# Summary

| Phase | Dates | Duration | Gate to advance |
| --- | --- | --- | --- |
| Phase 0 — Foundation & Validation | Jul 22 – Aug 11 | 3 weeks | 2 of 3 validation loops closed with real signal; compute story (user-provided vs. platform) explicitly decided; trivial end-to-end agent handoff runs |
| Phase 1 — Prove one domain end-to-end (Michaelis-Menten kinetics) | Aug 12 – Sep 22 | 6 weeks | Full agent chain, trust layer included, runs on real (non-synthetic) inputs; hallucination-check/critique demonstrably catch at least one real or planted error |
| Phase 2 — Expand to all six domains | Sep 23 – Nov 3 | 6 weeks | Shared pipeline proven reusable across all 6 domains with no per-domain architecture changes |
| Phase 3 — First paying pilot + hardening | Nov 4 – Dec 1 | 4 weeks | One named instructor/lab running Terrium in a real course or research setting under a real, even discounted, paid arrangement |
| December — Live pilot + Phase 4 begins | Dec 2 onward | ongoing | MVP declared complete; real usage data starts deciding the flagship domain, not further build sprints |

# Phase 0 — Foundation & Validation (Jul 22 – Aug 11, 3 weeks)

Gate: 2 of 3 outstanding validation emails (Prof. Tastan Bishop, Dr. Nayim, Dr. Ippoliti) answered with genuine signal; at least one professor directly asked whether they'd pay, not just whether they'd use it; the compute story (user-provided vs. platform-provided HPC/cloud) explicitly decided, since Phase 1's execution-agent design depends on the answer; and a trivial end-to-end agent handoff running in code.

| Week | Smyan (domain/product/validation) | Shanmuka (AI/ML lead) | Victor (backend) |
| --- | --- | --- | --- |
| Week 1 Jul 22–28 | Send/follow up all 3 validation emails; draft the explicit "would you pay" question, not just "would you use this"; start terrium.ai/.dev/.io + USPTO TESS trademark check | LiteLLM router config skeleton (model_list per agent role); stand up Ollama locally with llama3.2:3b | GitHub repo live (done); CI running pytest on push; confirm existing Google OAuth works end-to-end in a throwaway app |
| Week 2 Jul 29–Aug 4 | Second follow-up round on non-responsive contacts; draft the actual pilot offer — price, scope, semester timing, concretely | Pydantic schemas for Citation, Parameter, AgentHandoff; orchestrator retry/fail-loud behavior on validation errors | Postgres schema (runs, citations, user history) + SQLAlchemy models; Redis instance stood up for citation-lookup caching |
| Week 3 Aug 5–11 | Close the compute-story decision explicitly — this is a real product decision, not a formality | model_picker() + configuration_agent() as real async functions returning valid AgentHandoff objects; test with a real Michaelis-Menten question end to end | JupyterLite shell running locally with the Pyodide kernel; confirm numpy/scipy/matplotlib actually load in-browser |

Gate check, end of Week 3 Is 2 of 3 validation loops closed? Is the compute story decided? If not, this is where the schedule absorbs the delay — holding here an extra 3–5 days is cheaper than building Phase 1 on an undecided compute model and re-doing it in October.

# Phase 1 — Prove one domain end-to-end: Michaelis-Menten kinetics (Aug 12 – Sep 22, 6 weeks)

Kinetics is the obvious first domain: the BRENDA/KEGG literature-verification layer (brenda_client.py, enzyme_lookup.py, fallback_logic.py) already exists and passes 124 tests as of this session — a real, non-trivial head start for this domain's hallucination-check agent that none of the other five domains have yet.

Gate: the full agent chain, including the trust layer, runs successfully on real (not synthetic) inputs, with hallucination-check and critique demonstrably catching at least one real or deliberately planted error.

| Week | Smyan (domain/product/validation) | Shanmuka (AI/ML lead) | Victor (backend) |
| --- | --- | --- | --- |
| Week 4 Aug 12–18 | Write the equation-pinning reference doc for Michaelis-Menten — what constants, what scope, what a valid parameter looks like | Wire fallback_logic.resolve_kinetic_value in as the real literature backend for hallucination-check — the direct payoff of this session's scraper work | FastAPI skeleton stood up (orchestrator lives here); /simulate/kinetics/setup endpoint scaffolded |
| Week 5 Aug 19–25 | Recruit/confirm 5–10 real Michaelis-Menten test questions with known literature answers, for the Phase 1 gate | Hallucination-check agent implemented for real, routed to a different underlying model than configuration (per the router config already spec'd) | scipy.integrate.solve_ivp wired into the Pyodide execution path; confirm it runs client-side in an actual browser tab, not just a Python shell |
| Week 6 Aug 26–Sep 1 | Deliberately plant 2–3 wrong constants/citations into test inputs — the real adversarial data the Phase 1 gate requires | Critique agent (adversarial pass vs. cited sources) + correctness-verification agent (sanity ranges on Km/Vmax) | JupyterLite cells wired to render real interactive plots (Matplotlib/Plotly) from AgentHandoff output, not console text |
| Week 7 Sep 2–8 | Run the 5–10 real questions + 2–3 planted-error cases through the live system by hand; log every failure | Integration week: wire all 6 kinetics agents into one real orchestrator run, end to end | Integration week: same, backend/notebook side |
| Week 8 Sep 9–15 | Begin drafting the Phase 1 proof artifact (demo recording / notebook) for mentors and the pilot conversation | Bug-fix week on real failures from Week 7 — deliberately unstructured on purpose | Bug-fix week, same |
| Week 9 Sep 16–22 | Record the Phase 1 demo | Gate check: chain runs on all real inputs? Errors caught? | Buffer days built in here on purpose |

# Phase 2 — Expand to all six domains (Sep 23 – Nov 3, 6 weeks)

Gate: the shared pipeline proven reusable across all 6 domains with no per-domain architecture changes. Sequencing is deliberate — simplest execution tier first, hardest last, and each domain reuses plumbing proven in an earlier week rather than building fresh.

| Week | Smyan (domain/product/validation) | Shanmuka (AI/ML lead) | Victor (backend) |
| --- | --- | --- | --- |
| Weeks 10–11 Sep 23–Oct 6 | Equation-pinning reference docs for PCR and Monte Carlo, one week ahead of engineering — this is the actual Phase 2 bottleneck risk, not the code | PCR amplification configuration/equation-pinning (Tier 1 — pure Pyodide, reuses Phase 1's browser-execution plumbing directly) | Monte Carlo statistical simulation Pyodide wiring (Tier 1, parallel track to PCR) |
| Week 12 Oct 7–13 | Population genetics reference doc | Population genetics (Tier 1) — smallest domain, deliberately one week to create schedule slack after the two riskiest "does this generalize" domains | Same |
| Weeks 13–14 Oct 14–27 | SIR/SEIR reference doc | SIR/SEIR epidemiological modeling (Tier 2 — reuses the solve_ivp scaffolding built for kinetics in Phase 1 directly) | Same |
| Week 15 Oct 28–Nov 3 | Molecular dynamics reference doc — scope is GROMACS config generation, not execution (per spec, Terrium doesn't run MD directly) | Molecular dynamics setup-assist (Tier 3) — configuration generation + correctness-verification of that config, which is why this gets one week despite being the "hardest" domain on paper | FastAPI /simulate/md/setup endpoint, real GROMACS file generation |

The real Phase 2 risk It's Smyan's reference-doc work staying one week ahead of engineering, not the code itself. If a reference doc slips, the domain behind it slips with it — track this explicitly, don't let it hide inside a generic "on track" status.

# Phase 3 — First paying pilot + hardening (Nov 4 – Dec 1, 4 weeks)

Gate: one named instructor or teaching lab using Terrium in a real course or research setting, under a real — even discounted — paid arrangement.

| Week | Smyan (domain/product/validation) | Shanmuka (AI/ML lead) | Victor (backend) |
| --- | --- | --- | --- |
| Week 16 Nov 4–10 | Pilot instructor onboarded with real course material | Support real pilot usage; triage issues live | Redis caching tuned under real concurrent load for the first time — not synthetic load |
| Week 17 Nov 11–17 | Gather real instructor feedback | Patience-policy tuning (multi-minute literature search budgets) based on real usage patterns, not assumptions | Same |
| Week 18 Nov 18–24 | Prep investor/mentor demo narrative | Explain-Why UI and trust-trail visualization polish | Security/rate-limiting pass |
| Week 19 Nov 25–Dec 1 | Final MVP demo recording | Final bug-fix week | Final bug-fix week |

# December — live pilot, not more build sprints

MVP is declared complete December 1. December itself is real usage time from the paying pilot feeding Phase 4 ("let usage pick the flagship" — terrium_full.docx, section 2.5) — this is the actual point of finishing the build by December 1 rather than December 31: a full month of real engagement data before any decision about where to invest deeper.

# What could realistically push December

- Validation loops (Phase 0) not closing on schedule — this is the single most likely slip point, since it depends on three external people replying, not on Terrium's own team.

- The compute-story decision getting revisited mid-build instead of settled in Week 3 — this would force real rework in the execution agent, not just a delay.

- Phase 1's hallucination-check/critique gate not being cleanly demonstrable — this is the first real test of the whole trust-layer thesis, and if it needs real redesign rather than tuning, Phase 2's 6-week window assumes a working pattern to replicate 5 more times.

- Reference-doc work (Smyan) falling behind engineering in Phase 2 — flagged explicitly above because it's the quiet failure mode most likely to hide inside "on track" status updates.

None of these are reasons to compress the plan up front — they're the reasons weeks 3, 8–9, and 19 exist as absorption points rather than being scheduled as productive build time.

TERRIUM  |  MVP Development Timeline

Confidential  |  July 2026